## Sheet1
Informatio Need Description
Information Need | Are the level of staffing profile meet the need of project
Information Category | Resources and Cost
Measurable Concept
Measurable Concept | Development Effort
Entities and Attributes
Relevant Entities | Effort allocation to the staff
Attributes | The number of effort has been allocated
Base Measure Specification
Base Measures | The number of effort has been allocated
Measurement Methods | Count the number of effort has been allocated in the project time
Type of Method | Objective
Scale | Number
Type of Scale | Ordinal
Unit of Measurement | Staff-month
Derived Measure Specification
Derived Measure | The total number of effort allocation in the project
Measurement Function | Add every staff and number of months they worked in the team and add every staff-months number.
Indicator Specification
Indicator Description and Sample | Collect data by calculate project effort Need sample indicator
Analysis Model | The difference of plan effort allocation and actual effort allocation must be evaluated with a root-cause analysis
Decision Criteria | The difference of plan effort allocation and actual effort allocation is above 15% must be investigated for root cause and to determine if a new effort allocation plan is needed.
Indicator Interpretation | Need sample indicator interpretation
Data Collection Pprocedure
Frequency of Data Collection | Every two months
Responsible individual | Project manager
Phase or Activity in which Collected | During all over the project
Tools Used in Data Collection | N/A
Verification and Validation | N/A
Reponsitory for Collected Data | PSM Insight database
Data Analysis Procedure
Frequency of Data Reproting | Every two months
Responsible Individual | Project manager
Phase or Activity in which Analyzed | During all over the project
Source of Data for Analysis | PSM Insight database
Tools Used in Analysis | PSM Insight
Review, Report or User | 2-monthly report
Additional Information
Additional Analysis Guidance | Calculate the effort allocation should consider of the holiday of the schedule,
Implementation Considerations | Staff reports their effort every week is easier way to caculate the effort by project manager to check the details of staff effort allocation every two months.