## Sheet1
Informatio Need Description
Information Need | Is the increment 1 ready to begin operational test?
Information Category | Schedule and progress
Measurable Concept
Measurable Concept | Work Unit Progress
Entities and Attributes
Relevant Entities | Cases which are been test
Attributes | The number of test cases
Base Measure Specification
Base Measures | 1. The number of test cases which are planed 2. The number of test cases which are attempted 3. The number of test cases which are passed
Measurement Methods | Count the number of test cases which are planed, attempted and passed.
Type of Method | Objective
Scale | Number
Type of Scale | Ordinal
Unit of Measurement | Number of test cases
Derived Measure Specification
Derived Measure | 1. The ratio between passed number and attempted number 2. The ratio between passed number and planned number
Measurement Function | 1. Get the absolute of number of gap of attempted number and passed number, and use gap to divide to attempted number 2. Get the absolute of number of gap of planned number and passed number, and use gap to divide to planned
Indicator Specification
Indicator Description and Sample | Collect data by calculate number of test cases Need sample indicator
Analysis Model | 1.The low level of ratio of passed test cases and attempted one must be evaluated with a root-cause analysis 2. The low level of ratio of passed test cases and planned one must be evaluated with a root-cause analysis
Decision Criteria | The ratio is lower than 85%, it must be investigated for root cause
Indicator Interpretation | Need sample indicator interpretation
Data Collection Pprocedure
Frequency of Data Collection | Every two weeks
Responsible individual | Quality manager
Phase or Activity in which Collected | Evaluating readiness for test
Tools Used in Data Collection | N/A
Verification and Validation | N/A
Reponsitory for Collected Data | PSM Insight database
Data Analysis Procedure
Frequency of Data Reproting | Every two weeks
Responsible Individual | Quality manager
Phase or Activity in which Analyzed | Evaluating readiness for test
Source of Data for Analysis | PSM Insight database
Tools Used in Analysis | PSM Insight
Review, Report or User | Readiness for test report
Additional Information
Additional Analysis Guidance | Calculate the number of test cases should consider of the repeat one
Implementation Considerations | Test case writers could submits the report of test case statues to help manager to calculate this measurement