## Sheet1
Project | information needs | information categories | measureable concepts | proepective indicators

## Sheet2
Informatio Need Description
Information Need | Are the level of staffing profile meet the need of project
Information Category | Resources and Cost
Measurable Concept
Measurable Concept | Development Effort
Entities and Attributes
Relevant Entities | Effort allocation to the staff
Attributes | The number of effort has been allocated
Base Measure Specification
Base Measures | The number of effort has been allocated
Measurement Methods | Count the number of effort has been allocated in the project time
Type of Method | Objective
Scale | Number
Type of Scale | Ordinal
Unit of Measurement | Staff-month
Derived Measure Specification
Derived Measure | The total number of effort allocation in the project
Measurement Function | Add every staff and number of months they worked in the team and add every staff-months number.
Indicator Specification
Indicator Description and Sample | Collect data by calculate project effort Need sample indicator
Analysis Model | The difference of plan effort allocation and actual effort allocation must be evaluated with a root-cause analysis
Decision Criteria | The difference of plan effort allocation and actual effort allocation is above 15% must be investigated for root cause and to determine if a new effort allocation plan is needed.
Indicator Interpretation | Need sample indicator interpretation
Data Collection Pprocedure
Frequency of Data Collection | Every two months
Responsible individual | Project manager
Phase or Activity in which Collected | During all over the project
Tools Used in Data Collection | N/A
Verification and Validation | N/A
Reponsitory for Collected Data | PSM Insight database
Data Analysis Procedure
Frequency of Data Reproting | Every two months
Responsible Individual | Project manager
Phase or Activity in which Analyzed | During all over the project
Source of Data for Analysis | PSM Insight database
Tools Used in Analysis | PSM Insight
Review, Report or User | 2-monthly report
Additional Information
Additional Analysis Guidance | Calculate the effort allocation should consider of the holiday of the schedule,
Implementation Considerations | Staff reports their effort every week is easier way to caculate the effort by project manager to check the details of staff effort allocation every two months.

## Sheet3
Maturity type | Commerical/In-house | Contractor for military/Government 1110 | Military/Government agency 242
Not Given | 0% | 0% | 0%
Initial | 0% | 0% | 0%
Managed | 0% | 0% | 0%
Defined | 0% | 0% | 0%
Quantitatively | 0% | 0% | 0%
Optimizing | 0% | 0% | 0%

## Sheet4
Maturity type | 25 or fewer | 26 to 50 | 51 to 75 | 76 to 100 | 101 to 200
Not Given | 1.233% | 0.2782% | 0.2367% | 0.2367% | 0.2481%
Initial | 0.3083% | 0.1391% | 0.0789% | 0.0789% | 0.0827%
Managed | 13.87% | 3.199% | 1.894% | 1.736% | 1.489%
Defined | 15.42% | 10.02% | 5.365% | 5.128% | 5.624%
Quantitatively | 0% | 0.1391% | 0.1578% | 0.1578% | 0.1654%
Optimizing | 0.3083% | 0.1391% | 0.2367% | 0.5523% | 0.5789%
Maturity type | 201 to 300 | 301 to 500 | 501 to 1000 | 1001 to 2000 | 2000+
Not Given | 0.3156% | 0.3385% | 0.3385% | 0.3312% | 0.0564%
Initial | 0.0789% | 0.0677% | 0.0677% | 0% | 0.0564%
Managed | 1.578% | 0.2708% | 0.7447% | 0.207% | 0.3384%
Defined | 4.892% | 4.401% | 3.994% | 2.36% | 2.933%
Quantitatively | 0.3156% | 0.1354% | 0.1354% | 0% | 0.0564%
Optimizing | 0.8679% | 0.9478% | 1.557% | 1.242% | 2.369%

## Sheet5
Practice | Characterisation (FI, LI, PI, NI or NY | Strength(s)/Weakness(es) | Objective Evidence - Artifact, - Affirmation
RM SP 1.4